## times vertical
Base case/ Contingency | Sulcis Vertical Well |  | 1 | Offsshore1 | Offsshore2 | Offsshore3 | Offsshore4 | LandNL1 | LandNL2 | ITALY OFFSET 1 | EXPERIENCE | 1 | Expected time | Hrs selection | Days selection | Cumulative hours | Cumulative days | Depth
| Phase | Operations |  | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  | Hours | Hours | Days | Hours |  | mMDRT
B | 01__Rig move | Rig move to location | [10 empty] | 0 | 0 |  | 0 |  | 0
[16 empty] | 0 | 0 | 267
B | 03__Preparations | Preparations | [8 empty] | 6 |  | 6 | 6 | 0.25 | 6 | 0.25 | 0
[16 empty] | 6 | 0.25 | 267
B | 04__12 1/4" hole | P/U rockbit+stab+XO | [6 empty] | 1 |  |  |  | 1 | 1 | 0.041667 | 7 | 0.29167 | 0
B |  | Drill 16" hole | [10 empty] | 7 | 7 | 0.29167 | 14 | 0.58333 | 35
B |  | Length to drill | [10 empty] | 35 |  |  | 14 | 0.58333 | 35
B |  | Average speed (m/hr) | [10 empty] | 5 |  |  | 14 | 0.58333 | 35
B |  | pump hi-vis pills | [7 empty] | 0.25 |  |  | 0.2 | 0.2 | 0.0083333 | 14.2 | 0.59167 | 35
B |  | Circulating | [7 empty] | 0.5 |  |  | 0.5 | 0.5 | 0.020833 | 14.7 | 0.6125 | 35
B |  | Tripping | [7 empty] | 0.5 |  |  | 0.5 | 0.5 | 0.020833 | 15.2 | 0.63333 | 35
B |  | Reaming | [7 empty] | 0 |  |  | 0 | 0 |  | 15.2 | 0.63333 | 35
B |  | L/D BHA | [6 empty] | 2.25 | 1 |  |  | 1.6 | 1.6 | 0.066667 | 16.8 | 0.7 | 35
B |  | Other ops |  | 1 | 3 | 3 |  |  |  |  | 1 |  | 2 | 2 | 0.083333 | 18.8 | 0.78333 | 35
[16 empty] | 18.8 | 0.78333 | 267
C | 05__CONT:losses in conductor hole | Extra circulating and pumping pills in case of losses | [8 empty] | 4 |  | 4 | 4 | 0.16667 | 22.8 | 0.95 | 35
[16 empty] | 22.8 | 0.95 | 267
B | 07__9 5/8" csg | Install CAR system or eq. to top drive |  | 1 |  |  |  | 1 | 0.5 |  |  |  | 0.8 | 0.8 | 0.033333 | 23.6 | 0.98333 | 35
B |  | Install casing circulation tool | [5 empty] | 1 | 1 |  | 0.5 |  | 0.8 | 0.8 | 0.033333 | 24.4 | 1.0167 | 35
B |  | P/U & install csg tongs |  | 1.45 |  |  |  | 3 | 1 |  | 1 |  | 1.6 | 1.6 | 0.066667 | 26 | 1.0833 | 35
B |  | P/U & M/U csg S/T and next 2 joints, pipe lock | [6 empty] | 4 |  | 2 |  | 3 | 3 | 0.125 | 29 | 1.2083 | 35
B |  | P/U & install false rotary | [8 empty] | 1.5 |  | 1.5 | 1.5 | 0.0625 | 30.5 | 1.2708 | 35
B |  | RIH stinger to csg shoetrack | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 31 | 1.2917 | 35
B |  | Stag stinger in landing collar and break circulation | [8 empty] | 0.25 |  | 0.2 | 0.2 | 0.0083333 | 31.2 | 1.3 | 35
B |  | Circulation before cement job | [8 empty] | 0.1 |  | 0.1 | 0.1 | 0.0041667 | 31.3 | 1.3042 | 35
B |  | R/D equipment |  | 1 | 1 | 1 |  | 1 | 0.5 |  |  |  | 0.9 | 0.9 | 0.0375 | 32.2 | 1.3417 | 35
[16 empty] | 32.2 | 1.3417 | 267
B | 09__9 5/8" cement | R/U cement head | [5 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | 0.020833 | 32.7 | 1.3625 | 35
B |  | cement job | [8 empty] | 0.25 |  | 0.2 | 0.2 | 0.0083333 | 32.9 | 1.3708 | 35
B |  | WOC time | [10 empty] | 12 |  |  | 32.9 | 1.3708 | 35
B |  | (WOC starts) check for back pr, disconnect stinger | [7 empty] | 0.3 |  |  | 0.3 | 0.3 | 0.0125 | 33.2 | 1.3833 | 35
B |  | POOH stinger & L/D stinger RT | [8 empty] | 0.2 |  | 0.2 | 0.2 | 0.0083333 | 33.4 | 1.3917 | 35
B |  | R/D cement equipment | [5 empty] | 2 | 0.5 |  | 0.5 |  | 1 | 1 | 0.041667 | 34.4 | 1.4333 | 35
B |  | P/U & M/U DP & set back |  | 6.5 | 9 | 14.5 |  |  |  | 5 | [5 empty] | 34.4 | 1.4333 | 35
B |  | Length to M/U |  | 440 | 946 | 810 |  |  |  | 650 | [5 empty] | 34.4 | 1.4333 | 35
B |  | Average speed (m/hr) |  | 67.6923 | 105.1111 | 55.8621 |  |  |  | 130 |  |  | RIH5DPsingles |  |  | 34.4 | 1.4333 | 35
B |  | Clean area around conductor | [5 empty] | 3 | 2 |  |  |  | 2.5 | 2.5 | 0.10417 | 36.9 | 1.5375 | 35
B |  | Complete remaining WOC time | [10 empty] | -1 | -1 |  | 35.9 | 1.4958 | 35
[16 empty] | 35.9 | 1.4958 | 267
C | 11__CONT:no conductor cement at surface | Fill up annulus 16" x 13 3/8" if necessary | [8 empty] | 8 |  | 8 | 8 | 0.33333 | 43.9 | 1.8292 | 35
[16 empty] | 43.9 | 1.8292 | 267
B | 13__install diverter | cut conductor pipe | [7 empty] | 2 |  |  | 2 | 2 | 0.083333 | 45.9 | 1.9125 | 35
B |  | Install diverter & test same | [7 empty] | 6 |  |  | 6 | 6 | 0.25 | 51.9 | 2.1625 | 35
[16 empty] | 51.9 | 2.1625 | 267
B | 14__ 8 1/2" hole to top core | P/U rockbit+stab+XO (80m) | [6 empty] | 1 |  |  |  | 1 | 1 | 0.041667 | 52.9 | 2.2042 | 35
B |  | Drill out stinger recepticle, circulate | [7 empty] | 1 |  |  | 1 | 1 | 0.041667 | 53.9 | 2.2458 | 35
B |  | Clear rathole |  | 0.5 | 0.5 | 2 |  | 0.5 |  |  |  |  | 0.8 | 0.8 | 0.033333 | 54.7 | 2.2792 | 35
B |  | Flowcheck | [5 empty] | 0.5 |  |  | 0.25 |  | 0.3 | 0.3 | 0.0125 | 55 | 2.2917 | 35
B |  | Drill 12 1/4" hole | [10 empty] | 2.6 | 2.6 | 0.10833 | 57.6 | 2.4 | 61
B |  | Length to drill | [10 empty] | 26 |  |  | 57.6 | 2.4 | 61
B |  | Average speed (m/hr) | [10 empty] | 10 |  |  | 57.6 | 2.4 | 61
B |  | Circulating | [8 empty] | 1 |  | 1 | 1 | 0.041667 | 58.6 | 2.4417 | 61
B |  | Flowcheck | [5 empty] | 0.5 |  |  | 0.25 |  | 0.3 | 0.3 | 0.0125 | 58.9 | 2.4542 | 61
B |  | POOH BHA | [10 empty] | 0.67778 | 0.67778 | 0.028241 | 59.5778 | 2.4824 | 61
B |  | Length to POOH | [10 empty] | 61 |  |  | 59.5778 | 2.4824 | 61
B |  | Average speed (m/hr) | [10 empty] | 90 |  |  | 59.5778 | 2.4824 | 61
B |  | L/O BHA | [6 empty] | 2.25 | 1 |  |  | 1.6 | 1.6 | 0.066667 | 61.1778 | 2.5491 | 61
B |  | Other ops |  | 0.5 | 4.5 |  |  | 1 |  | 2 |  |  | 2 | 2 | 0.083333 | 63.1778 | 2.6324 | 61
[16 empty] | 63.1778 | 2.6324 | 61
C | 20__CONT:tight 8 1/2"hole | Extra reaming necessary in case of hole stability issues | [8 empty] | 2 |  | 2 | 2 | 0.083333 | 65.1778 | 2.7157 | 61
[16 empty] | 65.1778 | 2.7157 | 61
B | 21__8 1/2" core1 | P/U & M/U coring BHA | [5 empty] | 2.75 |  | 3.5 | 1.5 |  | 2.5 | 2.5 | 0.10417 | 67.6778 | 2.8199 | 61
B |  | RIH coring BHA | [7 empty] | 12 |  |  | 0.37778 | 0.37778 | 0.015741 | 68.0556 | 2.8356 | 61
B |  | Length to RIH | [7 empty] | 3817 |  |  | 34 |  |  | 68.0556 | 2.8356 | 61
B |  | Average speed (m/hr) | [7 empty] | 318.0833 | 0 |  | 90 |  |  | 68.0556 | 2.8356 | 61
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 68.5556 | 2.8565 | 61
B |  | Drop ball to activate coring | [5 empty] | 0.75 |  |  | 0.1 |  | 0.4 | 0.4 | 0.016667 | 68.9556 | 2.8731 | 61
B |  | Core hole | [5 empty] | 12 |  | 24.5 |  |  | 5.4 | 5.4 | 0.225 | 74.3556 | 3.0981 | 88
B |  | Length to core | [5 empty] | 54 |  | 27 |  |  | 27 |  |  | 74.3556 | 3.0981 | 88
B |  | Average speed (m/hr) | [5 empty] | 4.5 |  | 1.102 |  |  | 5 |  |  | 74.3556 | 3.0981 | 88
B |  | Circulating | [5 empty] | 0.5 |  | 1 | 0.5 |  | 0.6 | 0.6 | 0.025 | 74.9556 | 3.1231 | 88
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 75.4556 | 3.144 | 88
B |  | POOH coring BHA | [5 empty] | 1 |  | 13 |  |  | 1 | 1 | 0.041667 | 76.4556 | 3.1856 | 88
B |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 61 |  |  | 76.4556 | 3.1856 | 88
B |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 60 |  |  | 76.4556 | 3.1856 | 88
B |  | L/O BHA, recovering coring barrell | [5 empty] | 2 |  | 5.5 |  |  | 3.7 | 3.7 | 0.15417 | 80.1556 | 3.3398 | 88
B |  | Other ops | [5 empty] | 1 |  | 1.5 | 0.5 |  | 1 | 1 | 0.041667 | 81.1556 | 3.3815 | 88
[16 empty] | 81.1556 | 3.3815 | 61
B | 22__8 1/2" core2 | P/U & M/U coring BHA | [5 empty] | 2.75 |  | 3.5 | 1.5 |  | 2.5 | 2.5 | 0.10417 | 83.6556 | 3.4856 | 88
B |  | RIH coring BHA | [7 empty] | 12 |  |  | 0.67778 | 0.67778 | 0.028241 | 84.3333 | 3.5139 | 88
B |  | Length to RIH | [7 empty] | 3817 |  |  | 61 |  |  | 84.3333 | 3.5139 | 88
B |  | Average speed (m/hr) | [7 empty] | 318.0833 | 0 |  | 90 |  |  | 84.3333 | 3.5139 | 88
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 84.8333 | 3.5347 | 88
B |  | Drop ball to activate coring | [5 empty] | 0.75 |  |  | 0.1 |  | 0.4 | 0.4 | 0.016667 | 85.2333 | 3.5514 | 88
B |  | Core hole | [5 empty] | 12 |  | 24.5 |  |  | 5.4 | 5.4 | 0.225 | 90.6333 | 3.7764 | 115
B |  | Length to core | [5 empty] | 54 |  | 27 |  |  | 27 |  |  | 90.6333 | 3.7764 | 115
B |  | Average speed (m/hr) | [5 empty] | 4.5 |  | 1.102 |  |  | 5 |  |  | 90.6333 | 3.7764 | 115
B |  | Circulating | [5 empty] | 0.5 |  | 1 | 0.5 |  | 0.6 | 0.6 | 0.025 | 91.2333 | 3.8014 | 115
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 91.7333 | 3.8222 | 115
B |  | POOH coring BHA | [5 empty] | 1 |  | 13 |  |  | 1.4 | 1.4 | 0.058333 | 93.1333 | 3.8806 | 115
B |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 88 |  |  | 93.1333 | 3.8806 | 115
B |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 60 |  |  | 93.1333 | 3.8806 | 115
B |  | L/O BHA, recovering coring barrell | [5 empty] | 2 |  | 5.5 |  |  | 3.7 | 3.7 | 0.15417 | 96.8333 | 4.0347 | 115
B |  | Other ops | [5 empty] | 1 |  | 1.5 | 0.5 |  | 1 | 1 | 0.041667 | 97.8333 | 4.0764 | 115
[16 empty] | 97.8333 | 4.0764 | 115
B | 23__8 1/2" core3 | P/U & M/U coring BHA | [5 empty] | 2.75 |  | 3.5 | 1.5 |  | 2.5 | 2.5 | 0.10417 | 100.3333 | 4.1806 | 115
B |  | RIH coring BHA | [7 empty] | 12 |  |  | 0.97778 | 0.97778 | 0.040741 | 101.3111 | 4.2213 | 115
B |  | Length to RIH | [7 empty] | 3817 |  |  | 88 |  |  | 101.3111 | 4.2213 | 115
B |  | Average speed (m/hr) | [7 empty] | 318.0833 | 0 |  | 90 |  |  | 101.3111 | 4.2213 | 115
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 101.8111 | 4.2421 | 115
B |  | Drop ball to activate coring | [5 empty] | 0.75 |  |  | 0.1 |  | 0.4 | 0.4 | 0.016667 | 102.2111 | 4.2588 | 115
B |  | Core hole | [5 empty] | 12 |  | 24.5 |  |  | 5.4 | 5.4 | 0.225 | 107.6111 | 4.4838 | 142
B |  | Length to core | [5 empty] | 54 |  | 27 |  |  | 27 |  |  | 107.6111 | 4.4838 | 142
B |  | Average speed (m/hr) | [5 empty] | 4.5 |  | 1.102 |  |  | 5 |  |  | 107.6111 | 4.4838 | 142
B |  | Circulating | [5 empty] | 0.5 |  | 1 | 0.5 |  | 0.6 | 0.6 | 0.025 | 108.2111 | 4.5088 | 142
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 108.7111 | 4.5296 | 142
B |  | POOH coring BHA | [5 empty] | 1 |  | 13 |  |  | 1.9 | 1.9 | 0.079167 | 110.6111 | 4.6088 | 142
B |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 115 |  |  | 110.6111 | 4.6088 | 142
B |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 60 |  |  | 110.6111 | 4.6088 | 142
B |  | L/O BHA, recovering coring barrell | [5 empty] | 2 |  | 5.5 |  |  | 3.7 | 3.7 | 0.15417 | 114.3111 | 4.763 | 142
B |  | Other ops | [5 empty] | 1 |  | 1.5 | 0.5 |  | 1 | 1 | 0.041667 | 115.3111 | 4.8046 | 142
[16 empty] | 115.3111 | 4.8046 | 142
B | 24__8 1/2" core4 | P/U & M/U coring BHA | [5 empty] | 2.75 |  | 3.5 | 1.5 |  | 2.5 | 2.5 | 0.10417 | 117.8111 | 4.9088 | 142
B |  | RIH coring BHA | [7 empty] | 12 |  |  | 1.2778 | 1.2778 | 0.053241 | 119.0889 | 4.962 | 142
B |  | Length to RIH | [7 empty] | 3817 |  |  | 115 |  |  | 119.0889 | 4.962 | 142
B |  | Average speed (m/hr) | [7 empty] | 318.0833 | 0 |  | 90 |  |  | 119.0889 | 4.962 | 142
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 119.5889 | 4.9829 | 142
B |  | Drop ball to activate coring | [5 empty] | 0.75 |  |  | 0.1 |  | 0.4 | 0.4 | 0.016667 | 119.9889 | 4.9995 | 142
B |  | Core hole | [5 empty] | 12 |  | 24.5 |  |  | 5.4 | 5.4 | 0.225 | 125.3889 | 5.2245 | 169
B |  | Length to core | [5 empty] | 54 |  | 27 |  |  | 27 |  |  | 125.3889 | 5.2245 | 169
B |  | Average speed (m/hr) | [5 empty] | 4.5 |  | 1.102 |  |  | 5 |  |  | 125.3889 | 5.2245 | 169
B |  | Circulating | [5 empty] | 0.5 |  | 1 | 0.5 |  | 0.6 | 0.6 | 0.025 | 125.9889 | 5.2495 | 169
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 126.4889 | 5.2704 | 169
B |  | POOH coring BHA | [5 empty] | 1 |  | 13 |  |  | 2.3 | 2.3 | 0.095833 | 128.7889 | 5.3662 | 169
B |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 142 |  |  | 128.7889 | 5.3662 | 169
B |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 60 |  |  | 128.7889 | 5.3662 | 169
B |  | L/O BHA, recovering coring barrell | [5 empty] | 2 |  | 5.5 |  |  | 3.7 | 3.7 | 0.15417 | 132.4889 | 5.5204 | 169
B |  | Other ops | [5 empty] | 1 |  | 1.5 | 0.5 |  | 1 | 1 | 0.041667 | 133.4889 | 5.562 | 169
[16 empty] | 133.4889 | 5.562 | 169
B | 25__8 1/2" core5 | P/U & M/U coring BHA | [5 empty] | 2.75 |  | 3.5 | 1.5 |  | 2.5 | 2.5 | 0.10417 | 135.9889 | 5.6662 | 169
B |  | RIH coring BHA | [7 empty] | 12 |  |  | 1.5778 | 1.5778 | 0.065741 | 137.5667 | 5.7319 | 169
B |  | Length to RIH | [7 empty] | 3817 |  |  | 142 |  |  | 137.5667 | 5.7319 | 169
B |  | Average speed (m/hr) | [7 empty] | 318.0833 | 0 |  | 90 |  |  | 137.5667 | 5.7319 | 169
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 138.0667 | 5.7528 | 169
B |  | Drop ball to activate coring | [5 empty] | 0.75 |  |  | 0.1 |  | 0.4 | 0.4 | 0.016667 | 138.4667 | 5.7694 | 169
B |  | Core hole | [5 empty] | 12 |  | 24.5 |  |  | 5.4 | 5.4 | 0.225 | 143.8667 | 5.9944 | 196
B |  | Length to core | [5 empty] | 54 |  | 27 |  |  | 27 |  |  | 143.8667 | 5.9944 | 196
B |  | Average speed (m/hr) | [5 empty] | 4.5 |  | 1.102 |  |  | 5 |  |  | 143.8667 | 5.9944 | 196
B |  | Circulating | [5 empty] | 0.5 |  | 1 | 0.5 |  | 0.6 | 0.6 | 0.025 | 144.4667 | 6.0194 | 196
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 144.9667 | 6.0403 | 196
B |  | POOH coring BHA | [5 empty] | 1 |  | 13 |  |  | 2.8 | 2.8 | 0.11667 | 147.7667 | 6.1569 | 196
B |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 169 |  |  | 147.7667 | 6.1569 | 196
B |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 60 |  |  | 147.7667 | 6.1569 | 196
B |  | L/O BHA, recovering coring barrell | [5 empty] | 2 |  | 5.5 |  |  | 3.7 | 3.7 | 0.15417 | 151.4667 | 6.3111 | 196
B |  | Other ops | [5 empty] | 1 |  | 1.5 | 0.5 |  | 1 | 1 | 0.041667 | 152.4667 | 6.3528 | 196
[16 empty] | 152.4667 | 6.3528 | 196
B | 26__8 1/2" core6 | P/U & M/U coring BHA | [5 empty] | 2.75 |  | 3.5 | 1.5 |  | 2.5 | 2.5 | 0.10417 | 154.9667 | 6.4569 | 196
B |  | RIH coring BHA | [7 empty] | 12 |  |  | 1.8778 | 1.8778 | 0.078241 | 156.8444 | 6.5352 | 196
B |  | Length to RIH | [7 empty] | 3817 |  |  | 169 |  |  | 156.8444 | 6.5352 | 196
B |  | Average speed (m/hr) | [7 empty] | 318.0833 | 0 |  | 90 |  |  | 156.8444 | 6.5352 | 196
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 157.3444 | 6.556 | 196
B |  | Drop ball to activate coring | [5 empty] | 0.75 |  |  | 0.1 |  | 0.4 | 0.4 | 0.016667 | 157.7444 | 6.5727 | 196
B |  | Core hole | [5 empty] | 12 |  | 24.5 |  |  | 5.4 | 5.4 | 0.225 | 163.1444 | 6.7977 | 223
B |  | Length to core | [5 empty] | 54 |  | 27 |  |  | 27 |  |  | 163.1444 | 6.7977 | 223
B |  | Average speed (m/hr) | [5 empty] | 4.5 |  | 1.102 |  |  | 5 |  |  | 163.1444 | 6.7977 | 223
B |  | Circulating | [5 empty] | 0.5 |  | 1 | 0.5 |  | 0.6 | 0.6 | 0.025 | 163.7444 | 6.8227 | 223
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 164.2444 | 6.8435 | 223
B |  | POOH coring BHA | [5 empty] | 1 |  | 13 |  |  | 3.2 | 3.2 | 0.13333 | 167.4444 | 6.9769 | 223
B |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 196 |  |  | 167.4444 | 6.9769 | 223
B |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 60 |  |  | 167.4444 | 6.9769 | 223
B |  | L/O BHA, recovering coring barrell | [5 empty] | 2 |  | 5.5 |  |  | 3.7 | 3.7 | 0.15417 | 171.1444 | 7.131 | 223
B |  | Other ops | [5 empty] | 1 |  | 1.5 | 0.5 |  | 1 | 1 | 0.041667 | 172.1444 | 7.1727 | 223
[16 empty] | 172.1444 | 7.1727 | 223
B | 27__8 1/2" core7 | P/U & M/U coring BHA | [5 empty] | 2.75 |  | 3.5 | 1.5 |  | 2.5 | 2.5 | 0.10417 | 174.6444 | 7.2769 | 223
B |  | RIH coring BHA | [7 empty] | 12 |  |  | 2.1778 | 2.1778 | 0.090741 | 176.8222 | 7.3676 | 223
B |  | Length to RIH | [7 empty] | 3817 |  |  | 196 |  |  | 176.8222 | 7.3676 | 223
B |  | Average speed (m/hr) | [7 empty] | 318.0833 | 0 |  | 90 |  |  | 176.8222 | 7.3676 | 223
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 177.3222 | 7.3884 | 223
B |  | Drop ball to activate coring | [5 empty] | 0.75 |  |  | 0.1 |  | 0.4 | 0.4 | 0.016667 | 177.7222 | 7.4051 | 223
B |  | Core hole | [5 empty] | 12 |  | 24.5 |  |  | 5.4 | 5.4 | 0.225 | 183.1222 | 7.6301 | 250
B |  | Length to core | [5 empty] | 54 |  | 27 |  |  | 27 |  |  | 183.1222 | 7.6301 | 250
B |  | Average speed (m/hr) | [5 empty] | 4.5 |  | 1.102 |  |  | 5 |  |  | 183.1222 | 7.6301 | 250
B |  | Circulating | [5 empty] | 0.5 |  | 1 | 0.5 |  | 0.6 | 0.6 | 0.025 | 183.7222 | 7.6551 | 250
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 184.2222 | 7.6759 | 250
B |  | POOH coring BHA | [5 empty] | 1 |  | 13 |  |  | 3.7 | 3.7 | 0.15417 | 187.9222 | 7.8301 | 250
B |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 223 |  |  | 187.9222 | 7.8301 | 250
B |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 60 |  |  | 187.9222 | 7.8301 | 250
B |  | L/O BHA, recovering coring barrell | [5 empty] | 2 |  | 5.5 |  |  | 3.7 | 3.7 | 0.15417 | 191.6222 | 7.9843 | 250
B |  | Other ops | [5 empty] | 1 |  | 1.5 | 0.5 |  | 1 | 1 | 0.041667 | 192.6222 | 8.0259 | 250
[16 empty] | 192.6222 | 8.0259 | 250
C | 29__CONT:need extra coring run | P/U & M/U coring BHA | [5 empty] | 2.75 |  | 3.5 | 1.5 |  | 2.5 | 2.5 | 0.10417 | 195.1222 | 8.1301 | 250
C |  | RIH coring BHA | [7 empty] | 12 |  |  | 2.1778 | 2.1778 | 0.090741 | 197.3 | 8.2208 | 250
C |  | Length to RIH | [7 empty] | 3817 |  |  | 196 |  |  | 197.3 | 8.2208 | 250
C |  | Average speed (m/hr) | [7 empty] | 318.0833 | 0 |  | 90 |  |  | 197.3 | 8.2208 | 250
C |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 197.8 | 8.2417 | 250
C |  | Drop ball to activate coring | [5 empty] | 0.75 |  |  | 0.1 |  | 0.4 | 0.4 | 0.016667 | 198.2 | 8.2583 | 250
C |  | Core hole | [5 empty] | 12 |  | 24.5 |  |  | 5.4 | 5.4 | 0.225 | 203.6 | 8.4833 | 250
C |  | Length to core | [5 empty] | 54 |  | 27 |  |  | 27 |  |  | 203.6 | 8.4833 | 250
C |  | Average speed (m/hr) | [5 empty] | 4.5 |  | 1.102 |  |  | 5 |  |  | 203.6 | 8.4833 | 250
C |  | Circulating | [5 empty] | 0.5 |  | 1 | 0.5 |  | 0.6 | 0.6 | 0.025 | 204.2 | 8.5083 | 250
C |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 204.7 | 8.5292 | 250
C |  | POOH coring BHA | [5 empty] | 1 |  | 13 |  |  | 3.7 | 3.7 | 0.15417 | 208.4 | 8.6833 | 250
C |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 223 |  |  | 208.4 | 8.6833 | 250
C |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 60 |  |  | 208.4 | 8.6833 | 250
C |  | L/O BHA, recovering coring barrell | [5 empty] | 2 |  | 5.5 |  |  | 3.7 | 3.7 | 0.15417 | 212.1 | 8.8375 | 250
C |  | Other ops | [5 empty] | 1 |  | 1.5 | 0.5 |  | 1 | 1 | 0.041667 | 213.1 | 8.8792 | 250
[16 empty] | 213.1 | 8.8792 | 250
C | 30__CONT:Need wiper trip between coring runs | P/U & M/U BHA | [6 empty] | 3 |  | 3 |  | 3 | 3 | 0.125 | 216.1 | 9.0042 | 250
C |  | RIH to TD | [10 empty] | 1.1111 | 1.1111 | 0.046296 | 217.2111 | 9.0505 | 250
C |  | Length to RIH | [10 empty] | 100 |  |  | 217.2111 | 9.0505 | 250
C |  | Average speed (m/hr) | [10 empty] | 90 |  |  | 217.2111 | 9.0505 | 250
C |  | Circulate and pump slug |  | 2.5 |  | 2 |  |  |  |  | 1 |  | 1.8 | 1.8 | 0.075 | 219.0111 | 9.1255 | 250
C |  | POOH wiper BHA | [10 empty] | 1.1111 | 1.1111 | 0.046296 | 220.1222 | 9.1718 | 250
C |  | Length to POOH | [10 empty] | 100 |  |  | 220.1222 | 9.1718 | 250
C |  | Average speed (m/hr) | [10 empty] | 90 |  |  | 220.1222 | 9.1718 | 250
C |  | B/D BHA | [6 empty] | 2.3 | 1 |  |  | 1.6 | 1.6 | 0.066667 | 221.7222 | 9.2384 | 250
[16 empty] | 221.7222 | 9.2384 | 250
C | 31__CONT:Trip to cure losses | P/U & M/U BHA | [6 empty] | 3 |  | 3 |  | 3 | 3 | 0.125 | 224.7222 | 9.3634 | 250
C |  | RIH to TD | [10 empty] | 1.1111 | 1.1111 | 0.046296 | 225.8333 | 9.4097 | 250
C |  | Length to RIH | [10 empty] | 100 |  |  | 225.8333 | 9.4097 | 250
C |  | Average speed (m/hr) | [10 empty] | 90 |  |  | 225.8333 | 9.4097 | 250
C |  | Cure losses | [8 empty] | 5 |  | 5 | 5 | 0.20833 | 230.8333 | 9.6181 | 250
C |  | POOH BHA | [10 empty] | 1.1111 | 1.1111 | 0.046296 | 231.9444 | 9.6644 | 250
C |  | Length to POOH | [10 empty] | 100 |  |  | 231.9444 | 9.6644 | 250
C |  | Average speed (m/hr) | [10 empty] | 90 |  |  | 231.9444 | 9.6644 | 250
C |  | B/D BHA | [6 empty] | 2.3 | 1 |  |  | 1.6 | 1.6 | 0.066667 | 233.5444 | 9.731 | 250
[16 empty] | 221.7222 | 9.2384 | 250
B | 32__wiper run/drill to TD run | P/U & M/U wiper BHA | [5 empty] | 2.75 |  | 3.5 |  |  | 3.1 | 3.1 | 0.12917 | 224.8222 | 9.3676 | 250
B |  | RIH wiper BHA | [10 empty] | 1.1111 | 1.1111 | 0.046296 | 225.9333 | 9.4139 | 250
B |  | Length to RIH | [10 empty] | 100 |  |  | 225.9333 | 9.4139 | 250
B |  | Average speed (m/hr) | [10 empty] | 90 |  |  | 225.9333 | 9.4139 | 250
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 226.4333 | 9.4347 | 250
B |  | Ream | [8 empty] | 2 |  | 2 | 2 | 0.083333 | 228.4333 | 9.5181 | 250
B |  | Circulating | [8 empty] | 1 |  | 1 | 1 | 0.041667 | 229.4333 | 9.5597 | 250
B |  | Continue drilling 12 1/4" hole from bottom core to well TD | [10 empty] | 0 | 0 |  | 229.4333 | 9.5597 | 250
B |  | Length to drill from critical point | [10 empty] | 0 |  |  | 229.4333 | 9.5597 | 250
B |  | Average speed (m/hr) | [10 empty] | 10 |  |  | 229.4333 | 9.5597 | 250
B |  | Circulating | [8 empty] | 1 |  | 1 | 1 | 0.041667 | 230.4333 | 9.6014 | 250
B |  | Flowchecks | [8 empty] | 0.5 |  | 0.5 | 0.5 | 0.020833 | 230.9333 | 9.6222 | 250
B |  | POOH wiper BHA on stands | [5 empty] | 1 |  | 13 |  |  | 1.1 | 1.1 | 0.045833 | 232.0333 | 9.6681 | 250
B |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 100 |  |  | 232.0333 | 9.6681 | 250
B |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 90 |  |  | 232.0333 | 9.6681 | 250
B |  | L/O BHA | [8 empty] | 2 |  | 2 | 2 | 0.083333 | 234.0333 | 9.7514 | 250
B |  | Other ops | [5 empty] | 1 |  | 2 |  |  | 1.5 | 1.5 | 0.0625 | 235.5333 | 9.8139 | 250
[16 empty] | 235.5333 | 9.8139 | 250
B | 34__Logging all runs | R/U logging equipment |  | 1.5 | 3 | 2.5 | 1 | 2.5 | 2 |  |  |  | 2 | 2 | 0.083333 | 237.5333 | 9.8972 | 250
B |  | Perform Logs (sum of several logging runs) | [10 empty] | 3 | 3 | 0.125 | 240.5333 | 10.0222 | 250
B |  | R/D logging equipment |  | 1.5 |  | 1.5 | 1 | 1 | 1.5 |  |  |  | 1.3 | 1.3 | 0.054167 | 241.8333 | 10.0764 | 250
[16 empty] | 241.8333 | 10.0764 | 250
C | 36__CONT:Need wiper trip between WL runs | P/U & M/U BHA (80m) | [6 empty] | 3 |  | 3 |  | 3 | 3 | 0.125 | 244.8333 | 10.2014 | 250
C |  | Round trip in OH | [10 empty] | 1.1111 | 1.1111 | 0.046296 | 245.9444 | 10.2477 | 250
C |  | Length to RIH | [10 empty] | 100 |  |  | 245.9444 | 10.2477 | 250
C |  | Average speed (m/hr) | [10 empty] | 90 |  |  | 245.9444 | 10.2477 | 250
C |  | Circulate and pump slug |  | 2.5 |  | 2 |  |  |  |  | 1 |  | 1.8 | 1.8 | 0.075 | 247.7444 | 10.3227 | 250
C |  | Round trip in OH once at shoe - POOH | [10 empty] | 1.1111 | 1.1111 | 0.046296 | 248.8556 | 10.369 | 250
C |  | Length to POOH | [10 empty] | 100 |  |  | 248.8556 | 10.369 | 250
C |  | Average speed (m/hr) | [10 empty] | 90 |  |  | 248.8556 | 10.369 | 250
C |  | POOH BHA | [6 empty] | 2.3 | 1 |  |  | 1.6 | 1.6 | 0.066667 | 250.4556 | 10.4356 | 250
[16 empty] | 250.4556 | 10.4356 | 250
B | 42__6 5/8" csg | Install CARS system to top drive |  |  |  |  | 1 | 1.5 | 2 | 2.5 | 0.5 |  | 1.5 | 1.5 | 0.0625 | 251.9556 | 10.4981 | 250
B |  | Install casing circulation tool | [5 empty] | 1 | 1 |  |  |  | 1 | 1 | 0.041667 | 252.9556 | 10.5398 | 250
B |  | P/U and set up Weatherford casing tongs | [5 empty] | 3 | 4 | 3.5 |  |  | 3.5 | 3.5 | 0.14583 | 256.4556 | 10.6856 | 250
B |  | M/U csg shoetrack, pipelock and test floats | [8 empty] | 1 |  | 1 | 1 | 0.041667 | 257.4556 | 10.7273 | 250
B |  | Install electrodes total time | [10 empty] | 10 | 10 | 0.41667 | 267.4556 | 11.144 | 250
B |  | Connect electrodes cable total time | [10 empty] | 3 | 3 | 0.125 | 270.4556 | 11.269 | 250
B |  | RIH csg filling every joint WITH LINE | [10 empty] | 3.5 | 3.5 | 0.14583 | 273.9556 | 11.4148 | 250
B |  | Length to RIH | [10 empty] | 245 |  |  | 273.9556 | 11.4148 | 250
B |  | Average speed (m/hr) | [10 empty] | 70 |  |  | 273.9556 | 11.4148 | 250
B |  | Wash casing last 2 joints | [7 empty] | 0.5 |  |  | 0.5 | 0.5 | 0.020833 | 274.4556 | 11.4356 | 250
B |  | Circulated w/ csg circ tool packer and conditionated mud | [5 empty] | 2.5 |  | 2.5 |  |  | 2.5 | 2.5 | 0.10417 | 276.9556 | 11.5398 | 250
B |  | R/D csg running equipment (after cement job) |  | 1 | 1 | 1 |  | 1 | 3.5 |  |  |  | 1.5 | 1.5 | 0.0625 | 278.4556 | 11.6023 | 250
B |  | R/D csg circulation tool |  | 0.5 |  |  |  | 0.5 |  | 1 |  |  | 0.6 | 0.6 | 0.025 | 279.0556 | 11.6273 | 250
[16 empty] | 279.0556 | 11.6273 | 250
B | 44__6 5/8" cement | M/U cement head |  | 1 | 3 | 0.5 | 2.5 | 1.5 | 0.5 | 2 | 1.5 |  | 1.5 | 1.5 | 0.0625 | 280.5556 | 11.6898 | 250
B |  | circulation before cementing | [5 empty] | 0 |  | 0 |  |  | 0 | 0 |  | 280.5556 | 11.6898 | 250
B |  | cement job | [5 empty] | 2 | 1 | 1 |  |  | 1.3 | 1.3 | 0.054167 | 281.8556 | 11.744 | 250
B |  | WOC time | [10 empty] | 12 |  |  | 281.8556 | 11.744 | 250
B |  | wet pressure test | [7 empty] | 0.5 |  |  | 0.5 | 0.5 | 0.020833 | 282.3556 | 11.7648 | 250
B |  | R/D cement equipment (start WOC time) |  | 1.5 | 0 |  |  | 2 |  | 1 |  |  | 1.1 | 1.1 | 0.045833 | 283.4556 | 11.8106 | 250
B |  | Prepare wellhead at cellar area |  | 1.5 | [8 empty] | 1.5 | 1.5 | 0.0625 | 284.9556 | 11.8731 | 250
B |  | Wash pits (NONE assumed done at end) | [7 empty] | 11 |  |  | 0 | 0 |  | 284.9556 | 11.8731 | 250
B |  | Complete remaining WOC time (NONE as install WH) |  | 1.5 | 0 |  |  | 2 |  |  |  |  | 0 | 0 |  | 284.9556 | 11.8731 | 250
[16 empty] | 284.9556 | 11.8731 | 250
C | 46__CONT:losses during 6 5/8" csg cement job | Prepare and RIH capillary hoses in B-annulus | [8 empty] | 5 |  | 5 | 5 | 0.20833 | 289.9556 | 12.0815 | 250
C |  | circulation before cementing | [8 empty] | 2 |  | 2 | 2 | 0.083333 | 291.9556 | 12.1648 | 250
C |  | cement job | [8 empty] | 3 |  | 3 | 3 | 0.125 | 294.9556 | 12.2898 | 250
C |  | Complete remaining WOC time (NONE as install WH) | [10 empty] | 0 | 0 |  | 294.9556 | 12.2898 | 250
[16 empty] | 294.9556 | 12.2898 | 250
B | 48__Install WH | N/D diverter from conductor | [5 empty] | 1 | 2 |  |  |  | 1.5 | 1.5 | 0.0625 | 296.4556 | 12.3523 | 250
B |  | N/D riser from diverter | [5 empty] | 1.5 | 1.5 |  |  |  | 1.5 | 1.5 | 0.0625 | 297.9556 | 12.4148 | 250
B |  | Remove diverter from Conductor & L/D same | [7 empty] | 6 | 3 |  | 4.5 | 4.5 | 0.1875 | 302.4556 | 12.6023 | 250
B |  | Clear wellhead area | [5 empty] | 3 |  |  | 0.5 |  | 1.7 | 1.7 | 0.070833 | 304.1556 | 12.6731 | 250
B |  | Install landing plate on conductor stump | [7 empty] | 2 | 0.5 |  | 1.2 | 1.2 | 0.05 | 305.3556 | 12.7231 | 250
B |  | Cut 6 5/8" conductor | [7 empty] | 2 | 0.5 |  | 1.2 | 1.2 | 0.05 | 306.5556 | 12.7731 | 250
B |  | Install WHH onto 6 5/8" csg stump | [5 empty] | 2.5 | 7.25 | 14.5 | 3 |  | 6.8 | 6.8 | 0.28333 | 313.3556 | 13.0565 | 250
B |  | Run gyro |  | 1 |  |  | 1 |  |  |  | 0.5 |  | 0.8 | 0.8 | 0.033333 | 314.1556 | 13.0898 | 250
[16 empty] | 314.1556 | 13.0898 | 250
B | 52__wireline CBL Logs | R/U logging equipment |  | 1.5 | 3 | 2.5 | 1 | 2.5 | 2 |  | 1.5 |  | 2 | 2 | 0.083333 | 316.1556 | 13.1731 | 250
B |  | Perform Logs wireline & USI logs | [10 empty] | 3 | 3 | 0.125 | 319.1556 | 13.2981 | 250
B |  | R/D logging equipment |  | 1.5 |  | 1.5 | 1 | 1 | 1.5 |  | 1.5 |  | 1.3 | 1.3 | 0.054167 | 320.4556 | 13.3523 | 250
[16 empty] | 320.4556 | 13.3523 | 250
B | 54__Run Completion | R/U automatic tongs | [8 empty] | 3 |  | 3 | 3 | 0.125 | 323.4556 | 13.4773 | 250
B |  | P/U and run completion tool | [8 empty] | 5 |  | 5 | 5 | 0.20833 | 328.4556 | 13.6856 | 250
B |  | P/U and run 2,375" tubing | [10 empty] | 4.1667 | 4.1667 | 0.17361 | 332.6222 | 13.8593 | 250
B |  | Length to RIH | [10 empty] | 250 |  |  | 332.6222 | 13.8593 | 250
B |  | Average speed (m/hr) | [10 empty] | 60 |  |  | 332.6222 | 13.8593 | 250
B |  | Install XT | [8 empty] | 10 |  | 10 | 10 | 0.41667 | 342.6222 | 14.2759 | 250
[16 empty] | 342.6222 | 14.2759 | 250
B | 99__Preparations to move | Preparations to move | [8 empty] | 6 |  | 6 | 6 | 0.25 | 348.6222 | 14.5259 | 250
250

## times deviated
Base case/ Contingency | Sulcis Deviated Well |  | 1 | Offsshore1 | Offsshore2 | Offsshore3 | Offsshore4 | LandNL1 | LandNL2 | ITALY OFFSET 1 | EXPERIENCE | 1 | This well | Hrs selection
| Phase | Operations |  | Hours | Hours | Hours | Hours | Hours | Hours | Hours | Hours |  | Hours | Hours
B | 01__Rig move | Rig move to location | [10 empty] | 0 | 0
B | 03__Preparations | Preparations | [8 empty] | 6 |  | 6 | 6
B | 04__16" hole | P/U rockbit+stab+XO | [6 empty] | 1 |  |  |  | 1 | 1
B |  | Drill 16" hole | [10 empty] | 7 | 7
B |  | Length to drill | [10 empty] | 35
B |  | Average speed (m/hr) | [10 empty] | 5
B |  | pump hi-vis pills | [7 empty] | 0.25 |  |  | 0.2 | 0.2
B |  | Circulating | [7 empty] | 0.5 |  |  | 0.5 | 0.5
B |  | Tripping | [7 empty] | 0.5 |  |  | 0.5 | 0.5
B |  | Reaming | [7 empty] | 0 |  |  | 0 | 0
B |  | L/D BHA | [6 empty] | 2.25 | 1 |  |  | 1.6 | 1.6
B |  | Other ops |  | 1 | 3 | 3 |  |  |  |  | 1 |  | 2 | 2
C | 05__CONT:losses in conductor hole | Extra circulating and pumping pills in case of losses | [8 empty] | 4 |  | 4 | 4
B | 07__13 3/8" csg | Install CAR system or eq. to top drive |  | 1 |  |  |  | 1 | 0.5 |  |  |  | 0.8 | 0.8
B |  | Install casing circulation tool | [5 empty] | 1 | 1 |  | 0.5 |  | 0.8 | 0.8
B |  | P/U & install csg tongs |  | 1.45 |  |  |  | 3 | 1 |  | 1 |  | 1.6 | 1.6
B |  | P/U & M/U csg S/T and next 2 joints, pipe lock | [6 empty] | 4 |  | 2 |  | 3 | 3
B |  | P/U & install false rotary | [8 empty] | 1.5 |  | 1.5 | 1.5
B |  | RIH stinger to csg shoetrack | [8 empty] | 0.5 |  | 0.5 | 0.5
B |  | Stag stinger in landing collar and break circulation | [8 empty] | 0.25 |  | 0.2 | 0.2
B |  | Circulation before cement job | [8 empty] | 0.1 |  | 0.1 | 0.1
B |  | R/D equipment |  | 1 | 1 | 1 |  | 1 | 0.5 |  |  |  | 0.9 | 0.9
B | 09__13 3/8" cement | R/U cement head | [5 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
B |  | cement job | [8 empty] | 0.25 |  | 0.2 | 0.2
B |  | WOC time | [10 empty] | 12
B |  | (WOC starts) check for back pr, disconnect stinger | [7 empty] | 0.3 |  |  | 0.3 | 0.3
B |  | POOH stinger & L/D stinger RT | [8 empty] | 0.2 |  | 0.2 | 0.2
B |  | R/D cement equipment | [5 empty] | 2 | 0.5 |  | 0.5 |  | 1 | 1
B |  | P/U & M/U DP & set back |  | 6.5 | 9 | 14.5 |  |  |  | 5
B |  | Length to M/U |  | 440 | 946 | 810 |  |  |  | 650 |  |  | 166
B |  | Average speed (m/hr) |  | 67.6923 | 105.1111 | 55.8621 |  |  |  | 130 |  |  | 90
B |  | Clean area around conductor | [5 empty] | 3 | 2 |  |  |  | 2.5 | 2.5
B |  | Complete remaining WOC time | [10 empty] | -1 | -1
C | 11__CONT:no conductor cement at surface | Fill up annulus 16" x 13 3/8" if necessary | [8 empty] | 8 |  | 8 | 8
B | 13__install diverter | cut conductor pipe | [7 empty] | 2 |  |  | 2 | 2
B |  | Install diverter & test same | [7 empty] | 6 |  |  | 6 | 6
B | 14__ 12.25" hole to critical point (where decision made to P&A & S/T) | P/U rockbit+stab+XO (80m) | [6 empty] | 1 |  |  |  | 1 | 1
B |  | Drill out stinger recepticle, circulate | [7 empty] | 1 |  |  | 1 | 1
B |  | Clear rathole |  | 0.5 | 0.5 | 2 |  | 0.5 |  |  |  |  | 0.8 | 0.8
B |  | Flowcheck | [5 empty] | 0.5 |  |  | 0.25 |  | 0.3 | 0.3
B |  | Drill 12 1/4" hole | [10 empty] | 2.5 | 2.5
B |  | Length to drill | [10 empty] | 25
B |  | Average speed (m/hr) | [10 empty] | 10
B |  | POOH BHA | [10 empty] | 0.66667 | 0.66667
B |  | Length to POOH | [10 empty] | 60
B |  | Average speed (m/hr) | [10 empty] | 90
B |  | L/O BHA | [6 empty] | 2.25 | 1 |  |  | 1.6 | 1.6
B |  | P/U & M/U bit + motor + 1 DCs, test same |  | 6.5 | 3.5 | 1 |  | 5 |  |  |  |  | 4 | 4
B |  | Clear rathole |  | 0.5 | 0.5 | 2 |  | 0.5 |  |  |  |  | 0.8 | 0.8
B |  | Flowcheck |  | 1.5 |  |  |  | 0.5 |  |  |  |  | 1 | 1
B |  | Start drilling, M/U BHA (100m tot) as progressing | [10 empty] | 1.4222 | 1.4222
B |  | Depth of critical point | [10 empty] | 128
B |  | Length to drill | [10 empty] | 90
B |  | Average speed (m/hr) | [10 empty] | 10
B |  | Drill hole | [10 empty] | 0 | 0
B |  | Length to drill | [10 empty] | 0
B |  | Average speed (m/hr) | [10 empty] | 10
B |  | Circulating | [5 empty] | 2 |  |  |  |  | 2 | 2
B |  | Flowchecks |  | 0.5 |  |  |  | 2 |  |  |  |  | 1.2 | 1.2
B |  | Reaming | [8 empty] | 2 |  | 2 | 2
C | 15__CONT:cannot follow directional programme (POOH BHA) | POOH BHA | [10 empty] | -0.24444 | -0.24444
C |  | Length to POOH | [10 empty] | -22
C |  | Average speed (m/hr) | [10 empty] | 90
C |  | L/O BHA |  | 4.5 | 3 | 3 |  | 2 |  | 7 |  |  | 3.9 | 3.9
C |  | Other ops |  | 0.5 | 4.5 |  |  | 1 |  | 2 |  |  | 2 | 2
C | 16__CONT:cannot follow directional programme (P&A hole) | P/U stinger | [8 empty] | 1 |  | 1 | 1
C |  | RIH stinger picking it up in singels | [10 empty] | 1.3222 | 1.3222
C |  | Length to RIH minus 1 joint DP | [10 empty] | 119
C |  | Average speed (m/hr) | [10 empty] | 90
C |  | Connect stinger to 1 joint DP | [8 empty] | 0.5 |  | 0.5 | 0.5
C |  | M/U cement head |  | 1 | 3 | 0.5 | 2.5 | 1.5 | 0.5 | 2 | 1.5 |  | 1.5 | 1.5
C |  | circulation before cementing | [8 empty] | 0.5 |  | 0.5 | 0.5
C |  | cement job | [5 empty] | 2 | 1 | 1 |  |  | 1.3 | 1.3
C |  | WOC time | [10 empty] | 12
C |  | POOH & L/D stinger (2.64 l/m MD*167m=440l / 36.6l/m OH cap=12m OK no need to top up) | [10 empty] | 1.3222 | 1.3222
C |  | Length to POOH | [10 empty] | 119
C |  | Average speed (m/hr) | [8 empty] | 250 |  | 90
C |  | R/D cement equipment (start WOC time) |  | 1.5 | 0 |  |  | 2 |  | 1 |  |  | 1.1 | 1.1
C |  | Remainder of WOC time |  | 0.5 | 4.5 |  |  | 1 |  | 2 |  |  | 12.2222 | 12.2222
C | 17__CONT:cannot follow directional programme (dress TOC) | P/U & M/U mill to dress TOC | [8 empty] | 2 |  | 2 | 2
C |  | Mill TOC to new KOP | [8 empty] | 5 |  | 5 | 5
C |  | Circulate cement out and flowcheck | [8 empty] | 2 |  | 2 | 2
C |  | POOH & L/O BHA | [8 empty] | 1 |  | 1 | 1
C |  | Other ops |  | 0.5 | 4.5 |  |  | 1 |  | 2 |  |  | 2 | 2
C | 18__CONT:cannot follow directional programme (S/T hole and drill to critical point) | P/U & M/U bit + motor + 1 DCs, test same |  | 6.5 | 3.5 | 1 |  | 5 |  |  |  |  | 4 | 4
C |  | Time drill to kick off |  | 21 | 9 | 5 | 7 | 11 |  |  |  |  | 10.6 | 10.6
C |  | Flowcheck |  | 1.5 |  |  |  | 0.5 |  |  |  |  | 1 | 1
C |  | Start drilling, M/U BHA (100m tot) as progressing |  | 25.5 | 51.5 | 21.5 |  | 21 |  |  |  |  | 9 | 9
C |  | Length to drill |  | 440 | 1368 | 451 |  | 441 |  |  |  |  | 90
C |  | Average speed (m/hr) |  | 17.2549 | 26.5631 | 20.9767 |  | 21 |  |  |  |  | 10
C |  | Continue drilling 12 1/4" hole following directional programme |  | 25.5 | 51.5 | 21.5 |  | 21 |  |  |  |  | -2.2 | -2.2
C |  | Length to drill to critical point |  | 440 | 1368 | 451 |  | 441 |  |  |  |  | -22
C |  | Average speed (m/hr) |  | 17.2549 | 26.5631 | 20.9767 |  | 21 |  |  |  |  | 10
C |  | Circulating | [8 empty] | 1 |  | 1 | 1
C |  | Flowchecks | [8 empty] | 0.5 |  | 0.5 | 0.5
B | 19__ 12.25" hole from critical point (assumed 100m from well TD) to top coring point | Continue drilling 12 1/4" hole from critical point |  | 25.5 | 51.5 | 21.5 |  | 21 |  |  |  |  | 11.7 | 11.7
B |  | Length to drill from critical point |  | 440 | 1368 | 451 |  | 441 |  |  |  |  | 117
B |  | Average speed (m/hr) |  | 17.2549 | 26.5631 | 20.9767 |  | 21 |  |  |  |  | 10
B |  | Circulating | [8 empty] | 1 |  | 1 | 1
B |  | Flowchecks | [8 empty] | 0.5 |  | 0.5 | 0.5
B |  | Reaming (minus already counted in hole 1) | [8 empty] | 1 |  | 1 | 1
B |  | POOH BHA | [10 empty] | 1.0556 | 1.0556
B |  | Length to POOH | [10 empty] | 95
B |  | Average speed (m/hr) | [10 empty] | 90
B |  | L/O BHA |  | 4.5 | 3 | 3 |  | 2 |  | 7 |  |  | 3.9 | 3.9
B |  | Other ops |  | 0.5 | 4.5 |  |  | 1 |  | 2 |  |  | 2 | 2
C | 20__CONT:tight 12.25"hole | Extra reaming necessary in case of hole stability issues | [8 empty] | 5 |  | 5 | 5
B | 21__12 1/4" core1 through faults | P/U & M/U coring BHA | [5 empty] | 2.75 |  | 3.5 |  |  | 3.1 | 3.1
B |  | RIH coring BHA on stands | [7 empty] | 12 |  |  | 1.4839 | 1.4839
B |  | Length to RIH | [7 empty] | 3817 |  |  | 236
B |  | Average speed (m/hr) | [7 empty] | 318.0833 | 0 |  | 159.0417
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5
B |  | Drop ball to activate coring | [5 empty] | 0.75 |  |  |  |  | 0.7 | 0.7
B |  | Core hole | [5 empty] | 12 |  | 24.5 |  |  | 1.8 | 1.8
B |  | Length to core | [5 empty] | 54 |  | 27 |  |  | 9
B |  | Average speed (m/hr) | [5 empty] | 4.5 |  | 1.102 |  |  | 5
B |  | Circulating | [5 empty] | 0.5 |  | 2.5 | 2 |  | 1.6 | 1.6
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5
B |  | POOH coring BHA on stands | [5 empty] | 1 |  | 13 |  |  | 1.5 | 1.5
B |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 254
B |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 161.8974
B |  | L/O BHA, recovering coring barrell | [5 empty] | 2 |  | 5.5 |  |  | 3.7 | 3.7
B |  | Other ops | [5 empty] | 1 |  | 2 |  |  | 1.5 | 1.5
B | 22__12 1/4" core2 through faults | P/U & M/U coring BHA | [5 empty] | 2.75 |  | 3.5 |  |  | 3.1 | 3.1
B |  | RIH coring BHA on stands | [7 empty] | 12 |  |  | 1.5405 | 1.5405
B |  | Length to RIH | [7 empty] | 3817 |  |  | 245
B |  | Average speed (m/hr) | [7 empty] | 318.0833 | 0 |  | 159.0417
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5
B |  | Drop ball to activate coring | [5 empty] | 0.75 |  |  |  |  | 0.7 | 0.7
B |  | Core hole | [5 empty] | 12 |  | 24.5 |  |  | 1.8 | 1.8
B |  | Length to core | [5 empty] | 54 |  | 27 |  |  | 9
B |  | Average speed (m/hr) | [5 empty] | 4.5 |  | 1.102 |  |  | 5
B |  | Circulating | [5 empty] | 0.5 |  | 2.5 | 2 |  | 1.6 | 1.6
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5
B |  | POOH coring BHA on stands | [5 empty] | 1 |  | 13 |  |  | 1.5 | 1.5
B |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 254
B |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 161.8974
B |  | L/O BHA, recovering coring barrell | [5 empty] | 2 |  | 5.5 |  |  | 3.7 | 3.7
B |  | Other ops | [5 empty] | 1 |  | 2 |  |  | 1.5 | 1.5
C | 24__CONT:need extra coring run | P/U & M/U coring BHA | [5 empty] | 2.75 |  | 3.5 |  |  | 3.1 | 3.1
C |  | RIH coring BHA on stands | [7 empty] | 12 |  |  | 1.5971 | 1.5971
C |  | Length to RIH | [7 empty] | 3817 |  |  | 254
C |  | Average speed (m/hr) | [7 empty] | 318.0833 | 0 |  | 159.0417
C |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5
C |  | Drop ball to activate coring | [5 empty] | 0.75 |  |  |  |  | 0.7 | 0.7
C |  | Core hole | [5 empty] | 12 |  | 24.5 |  |  | 1.8 | 1.8
C |  | Length to core (set to zero as already counted in base case) | [5 empty] | 54 |  | 27 |  |  | 9
C |  | Average speed (m/hr) | [5 empty] | 4.5 |  | 1.102 |  |  | 5
C |  | Circulating | [5 empty] | 0.5 |  | 2.5 | 2 |  | 1.6 | 1.6
C |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5
C |  | POOH coring BHA on stands | [5 empty] | 1 |  | 13 |  |  | 1.6 | 1.6
C |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 263
C |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 161.8974
C |  | L/O BHA, recovering coring barrell (set to zero as already counted in base case) | [8 empty] | 0 |  | 0 | 0
C |  | Other ops | [5 empty] | 1 |  | 2 |  |  | 1.5 | 1.5
C | 25__CONT:trip to cure losses | P/U & M/U BHA | [5 empty] | 2.75 |  | 3.5 |  |  | 3.1 | 3.1
C |  | RIH to TD | [10 empty] | 1.2778 | 1.2778
C |  | Length to RIH | [10 empty] | 115
C |  | Average speed (m/hr) | [10 empty] | 90
C |  | Cure losses | [8 empty] | 5 |  | 5 | 5
C |  | POOH BHA | [5 empty] | 1 |  | 13 |  |  | 1.2 | 1.2
C |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 116
C |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 90
C |  | B/D BHA | [6 empty] | 2.3 | 1 |  |  | 1.6 | 1.6
B | 26__wiper run/drill to TD run | P/U & M/U wiper BHA | [5 empty] | 2.75 |  | 3.5 |  |  | 3.1 | 3.1
B |  | RIH wiper BHA on stands | [10 empty] | 1.2778 | 1.2778
B |  | Length to RIH | [10 empty] | 115
B |  | Average speed (m/hr) | [10 empty] | 90
B |  | Flowcheck | [8 empty] | 0.5 |  | 0.5 | 0.5
B |  | Ream | [8 empty] | 2 |  | 2 | 2
B |  | Circulating | [8 empty] | 1 |  | 1 | 1
B |  | Continue drilling 12 1/4" hole from bottom core to well TD |  | 25.5 | 51.5 | 21.5 |  | 21 |  |  |  |  | 0.1 | 0.1
B |  | Length to drill from critical point |  | 440 | 1368 | 451 |  | 441 |  |  |  |  | 1
B |  | Average speed (m/hr) |  | 17.2549 | 26.5631 | 20.9767 |  | 21 |  |  |  |  | 10
B |  | Circulating | [8 empty] | 1 |  | 1 | 1
B |  | Flowchecks | [8 empty] | 0.5 |  | 0.5 | 0.5
B |  | POOH wiper BHA on stands | [5 empty] | 1 |  | 13 |  |  | 1.2 | 1.2
B |  | Length to POOH | [5 empty] | 190 |  | 3844 |  |  | 116
B |  | Average speed (m/hr) | [5 empty] | 190 |  | 295.6923 | 0 |  | 90
B |  | L/O BHA | [8 empty] | 2 |  | 2 | 2
B |  | Other ops | [5 empty] | 1 |  | 2 |  |  | 1.5 | 1.5
B | 28__Logging all runs | R/U logging equipment |  | 1.5 | 3 | 2.5 | 1 | 2.5 | 2 |  |  |  | 2 | 2
B |  | Perform Logs (sum of several logging runs) | [10 empty] | 5 | 5
B |  | R/D logging equipment |  | 1.5 |  | 1.5 | 1 | 1 | 1.5 |  |  |  | 1.3 | 1.3
C | 34__CONT:Need wiper trip between WL runs | P/U & M/U BHA (80m) | [6 empty] | 3 |  | 3 |  | 3 | 3
C |  | Round trip in OH | [10 empty] | 1.2889 | 1.2889
C |  | Length to RIH | [10 empty] | 116
C |  | Average speed (m/hr) | [10 empty] | 90
C |  | Circulate and pump slug |  | 2.5 |  | 2 |  |  |  |  | 1 |  | 1.8 | 1.8
C |  | Round trip in OH once at shoe - POOH | [10 empty] | 1.2889 | 1.2889
C |  | Length to POOH | [10 empty] | 116
C |  | Average speed (m/hr) | [10 empty] | 90
C |  | POOH BHA | [6 empty] | 2.3 | 1 |  |  | 1.6 | 1.6
B | 36__Pump sand plug | P/U drilling BHA | [6 empty] | 1 |  |  |  | 1 | 1
B |  | RIH BHA to TD | [10 empty] | 2.4 | 2.4
B |  | Length to RIH | [10 empty] | 216
B |  | Average speed (m/hr) | [10 empty] | 90
B |  | Pump sand plug | [8 empty] | 1 |  | 1 | 1
B |  | POOH BHA | [10 empty] | 2.4 | 2.4
B |  | Length to POOH | [10 empty] | 216
B |  | Average speed (m/hr) | [10 empty] | 90
B |  | L/D BHA | [8 empty] | 1 |  | 1 | 1
C | 38__CONT:6 5/8" csg failed run (POOH csg) | Install TESCO CARS system to top drive |  | 3 | 2.5 |  | 1 | 1.5 | 2 | 2.5 |  |  | 2 | 2
C |  | Install casing circulation tool | [5 empty] | 1 | 1 |  |  |  | 1 | 1
C |  | P/U and set up Weatherford casing tongs | [5 empty] | 3 | 4 | 3.5 |  |  | 3.5 | 3.5
C |  | M/U csg shoetrack, pipelock and test floats | [8 empty] | 1 |  | 1 | 1
C |  | Install geophones last 50m of casing | [10 empty] | 10 | 10
C |  | Connect geophones cable | [10 empty] | 3 | 3
C |  | Connect fibre optic DAS | [10 empty] | 3 | 3
C |  | RIH csg filling every joint WITH LINE | [10 empty] | 1.0345 | 1.0345
C |  | Depth of stuck casing | [10 empty] | 150
C |  | Length to RIH | [10 empty] | 145
C |  | Average speed (m/hr) | [10 empty] | 70
C |  | Attempt to circulate and pull free (unsuccessful) | [8 empty] | 6 |  | 6 | 6
C |  | POOH csg keeping hole full | [10 empty] | 2.0714 | 2.0714
C |  | Length to POOH (say csg stuck at 150m) | [10 empty] | 145
C |  | Average speed (m/hr) | [10 empty] | 70
C |  | Cut shoetrack joints and L/D same | [8 empty] | 6 |  | 6 | 6
C |  | R/D csg running equipment (after cement job) |  | 1 | 1 | 1 |  | 1 | 3.5 |  |  |  | 1.5 | 1.5
C |  | R/D csg circulation tool |  | 0.5 |  |  |  | 0.5 |  | 1 |  |  | 0.6 | 0.6
C | 40__CONT:6 5/8" csg failed run (wiper trip) | P/U & M/U BHA (80m) | [6 empty] | 3 |  | 3 |  | 3 | 3
C |  | Round trip in OH | [10 empty] | 1.2889 | 1.2889
C |  | Length to RIH | [10 empty] | 116
C |  | Average speed (m/hr) | [10 empty] | 90
C |  | Circulate and pump slug |  | 2.5 |  | 2 |  |  |  |  | 1 |  | 1.8 | 1.8
C |  | Round trip in OH once at shoe - POOH | [10 empty] | 1.2889 | 1.2889
C |  | Length to POOH | [10 empty] | 116
C |  | Average speed (m/hr) | [10 empty] | 90
C |  | POOH BHA | [6 empty] | 2.3 | 1 |  |  | 1.6 | 1.6
B | 42__6 5/8" csg | Install CARS system to top drive |  |  |  |  | 1 | 1.5 | 2 | 2.5 | 0.5 |  | 1.5 | 1.5
B |  | Install casing circulation tool | [5 empty] | 1 | 1 |  |  |  | 1 | 1
B |  | P/U and set up Weatherford casing tongs | [5 empty] | 3 | 4 | 3.5 |  |  | 3.5 | 3.5
B |  | M/U csg shoetrack, pipelock and test floats | [8 empty] | 1 |  | 1 | 1
B |  | Install geophones last 50m of casing | [10 empty] | 10 | 10
B |  | Connect geophones cable | [10 empty] | 3 | 3
B |  | Connect fibre optic DAS | [10 empty] | 3 | 3
B |  | RIH csg filling every joint WITH LINE | [10 empty] | 3.3286 | 3.3286
B |  | Length to RIH | [10 empty] | 233
B |  | Average speed (m/hr) | [10 empty] | 70
B |  | Wash casing last 2 joints | [7 empty] | 0.5 |  |  | 0.5 | 0.5
B |  | Circulated w/ csg circ tool packer and conditionated mud | [5 empty] | 2.5 |  | 2.5 |  |  | 2.5 | 2.5
B |  | R/D csg running equipment (after cement job) |  | 1 | 1 | 1 |  | 1 | 3.5 |  |  |  | 1.5 | 1.5
B |  | R/D csg circulation tool |  | 0.5 |  |  |  | 0.5 |  | 1 |  |  | 0.6 | 0.6
B | 44__6 5/8" cement | M/U cement head |  | 1 | 3 | 0.5 | 2.5 | 1.5 | 0.5 | 2 | 1.5 |  | 1.5 | 1.5
B |  | circulation before cementing | [5 empty] | 0 |  | 0 |  |  | 0 | 0
B |  | cement job | [5 empty] | 2 | 1 | 1 |  |  | 1.3 | 1.3
B |  | WOC time | [10 empty] | 12
B |  | wet pressure test | [7 empty] | 0.5 |  |  | 0.5 | 0.5
B |  | R/D cement equipment (start WOC time) |  | 1.5 | 0 |  |  | 2 |  | 1 |  |  | 1.1 | 1.1
B |  | Prepare wellhead at cellar area |  | 1.5 | [8 empty] | 1.5 | 1.5
B |  | Wash pits (NONE assumed done at end) | [7 empty] | 11 |  |  | 0 | 0
B |  | Complete remaining WOC time (NONE as install WH) |  | 1.5 | 0 |  |  | 2 |  |  |  |  | 0 | 0
C | 46__CONT:losses during 6 5/8" csg cement job | Prepare and RIH capillary hoses in B-annulus | [8 empty] | 5 |  | 5 | 5
C |  | circulation before cementing | [8 empty] | 2 |  | 2 | 2
C |  | cement job | [8 empty] | 3 |  | 3 | 3
C |  | WOC time (NONE as install WH) | [10 empty] | 0 | 0
B | 48__Install WH | N/D diverter from conductor | [5 empty] | 1 | 2 |  |  |  | 1.5 | 1.5
B |  | N/D riser from diverter | [5 empty] | 1.5 | 1.5 |  |  |  | 1.5 | 1.5
B |  | Remove diverter from Conductor & L/D same | [7 empty] | 6 | 3 |  | 4.5 | 4.5
B |  | Clear wellhead area | [5 empty] | 3 |  |  | 0.5 |  | 1.7 | 1.7
B |  | Install landing plate on conductor stump | [7 empty] | 2 | 0.5 |  | 1.2 | 1.2
B |  | Cut 6 5/8" conductor | [7 empty] | 2 | 0.5 |  | 1.2 | 1.2
B |  | Install WHH onto 6 5/8" csg stump | [5 empty] | 2.5 | 7.25 | 14.5 | 3 |  | 6.8 | 6.8
B |  | Reinstall diverter (as per given instructions, but it is strongly recommended to install BOP instead) | [7 empty] | 6 |  |  | 6 | 6
B |  | Install flow riser & coflex hose (NOT on this rig) | [5 empty] | 2 | 2.5 |  | 0 |  | 0 | 0
B |  | Run gyro |  | 1 |  |  | 1 |  |  |  | 0.5 |  | 0.8 | 0.8
B | 50__Remove sand plug | P/U stinger P/U & RIH wiper BHA | [8 empty] | 1 |  | 1 | 1
B |  | RIH BHA | [10 empty] | 2.4 | 2.4
B |  | Length to RIH | [10 empty] | 216
B |  | Average speed (m/hr) | [10 empty] | 90
B |  | Drill through shoetrack and cement | [8 empty] | 5 |  | 5 | 5
B |  | Circulate hole clean, removing sand plug (5xBU vol) | [10 empty] | 0.64305 | 0.64305
B |  | Well volume | [10 empty] | 6173.2488
B |  | Pumping speed (lpm) | [10 empty] | 800
B |  | Displace well to brine (Xantam gum puch pill) 5 X BU | [10 empty] | 0.64305 | 0.64305
B |  | Well volume | [10 empty] | 6173.2488
B |  | Pumping speed (lpm) | [10 empty] | 800
B |  | POOH BHA | [10 empty] | 2.4 | 2.4
B |  | Length to POOH | [10 empty] | 216
B |  | Average speed (m/hr) | [10 empty] | 90
B |  | L/D BHA | [8 empty] | 1 |  | 1 | 1
B | 52__wireline CBL Logs | R/U logging equipment |  | 1.5 | 3 | 2.5 | 1 | 2.5 | 2 |  | 1.5 |  | 2 | 2
B |  | Perform Logs wireline & USI logs | [10 empty] | 3 | 3
B |  | R/D logging equipment |  | 1.5 |  | 1.5 | 1 | 1 | 1.5 |  | 1.5 |  | 1.3 | 1.3
B | 54__Run Completion | R/U automatic tongs | [8 empty] | 3 |  | 3 | 3
B |  | P/U and run completion tool | [8 empty] | 5 |  | 5 | 5
B |  | P/U and run 2,375" tubing | [10 empty] | 3.75 | 3.75
B |  | Length to RIH | [10 empty] | 150
B |  | Average speed (m/hr) | [10 empty] | 40
B |  | connect Safety valve control line and land tubing hanger, R/D automatic tongs | [8 empty] | 7 |  | 7 | 7
B |  | circulate filtercake breaker fluid and set packer | [8 empty] | 5 |  | 5 | 5
B |  | remove Diverter | [8 empty] | 6 |  | 6 | 6
B |  | Install XT | [8 empty] | 10 |  | 10 | 10
B | 99__Preparations to move | Preparations to move | [8 empty] | 6 |  | 6 | 6

## costs vertical
once off (OO); time-dependent (TD); depth-dependent (DD) | Tangible (T); not-tangible (NT) | Spreadrate (S); drilling spreadrate (DS); G&A (GA); not spreadrate (N) | Class | Subclass | ITEM | UNIT (Well(WE), Item (EA), meters, etc) | Unit Price | Currency | Qty Description | Qty | Total in eur
[10 empty] | TOTAL --> | 1199826.178
OO | NT | N | 01 - LOCATION | Location preparation | Massenza rig | WE | 26000 | eur | 0 | 1 | 26000
OO | NT | N | 01 - LOCATION | Location restoration | Massenza rig | WE | 30000 | eur | 0 | 1 | 30000
OO | NT | N | 02 - MOB/DEMOB & RIG MOVE | MOB/DEMOB | Massenza rig | PR | 220000 | eur | Wells to drill | 0.5 | 110000
OO | NT | N | 02 - MOB/DEMOB & RIG MOVE | RIG MOVE | Massenza rig | WE | 35000 | eur | Wells to drill | 0.5 | 17500
TD | NT | S | 03 - RIG | RIG FUEL | Massenza rig | DAY | 1500 | eur | Total well time+Rig move time/2 | 14.3368 | 21505.1389
TD | NT | S | 03 - RIG | RIG RATE | Massenza rig | DAY | 9000 | eur | Total well time | 13.5868 | 122280.8333
OO | T | N | 04 - WELL TOP | WELLHEAD | Sulcis 13 3/8" WHH | WE | 30000 | eur | 0 | 1 | 30000
OO | T | N | 04 - WELL TOP | XMAS TREE | Sulcis 13 3/8" Xmas tree | WE | 30000 | eur | 0 | 1 | 30000
TD | NT | S | 04 - WELL TOP | XMAS TREE services | 1 operator including time | DAY | 1200 | eur | Xmas tree setting time + standby time | 3 | 3600
TD | NT | DS | 05 - CASING TUBULARS | CASING RUNNING PERSONNEL | Personnel | DAY | 3400 | eur | Casing Running Time + Time in between two casing runs+Standby time personnel | 10.7684 | 36612.6481
TD | NT | DS | 05 - CASING TUBULARS | CASING RUNNING Material - Standby | Tongs | DAY | 1125 | eur | Material standby time material upon arrival&departure and during drilling hole between two casing jobs | 10.8684 | 12226.9792
TD | NT | DS | 05 - CASING TUBULARS | CASING RUNNING Material - Operating | Tongs | DAY | 2250 | eur | Casing Running Time | 2 | 4500
DD | T | N | 05 - CASING TUBULARS | CASING tubular costs Section 1 | 9-5/8 47# P110 | M | 116 | usd | section 1 tubular length | 32 | 3118.08
DD | T | N | 05 - CASING TUBULARS | CASING tubular costs Section 2 | 6 5/8" 24# FIBER GLASS casing with ad hoc centralizer | M | 121 | usd | section 2 tubular length | 250 | 25410
OO | T | N | 06 - CASING-RELATED | CASING MATERIAL - OTHER | Float and shoetrack equipment | EA | 6000 | eur | Casing Sections | 2 | 12000
OO | T | N | 06 - CASING-RELATED | CASING Centralizers Section 1 | 9-5/8 47# P110 | EA | 175 | usd | section 1 centralisers # | 2.6667 | 392
OO | T | N | 06 - CASING-RELATED | CASING Centralizers Section 2 | 6 5/8" 24# FIBER GLASS casing with ad hoc centralizer | EA | 400 | usd | section 2 centralisers # | 13.8889 | 4666.6667
OO | NT | S | 07 - BITS | DRILLING BITS Section 2 | Sulcis vertical 8 1/2" 4.4.7 | EA | 5500 | eur | 0 | 1 | 5500
OO | NT | DS | 08 - FISHING | Fishing tools package on site | Vertical well 8 1/2" to 250m + 6 5/8" csg | WE | 21500 | eur | 1 | 1 | 21500
TD | NT | DS | 09 - DRILLING | Extra 2 7/8" or 2 3/8" DP daily rental | 4eur/joint/day | DAY | 131.7333 | eur | Total welltime + rigmove time | 15.0868 | 1987.4291
OO | NT | S | 09 - DRILLING | Extra 2 7/8" or 2 3/8" DP final inspection (at end of all wells) | Xovers and subs | ea | 3000 | eur | Divided by number of wells | 0.5 | 1500
DD | NT | S | 09 - DRILLING | WATER | Water supply | M3 | 10 | eur | Total cubic meters | 191.7541 | 1917.5415
TD | NT | S | 09 - DRILLING | Rome soap dope | Rome soap dope | DAY | 100 | eur | Total drilling time | 11.9284 | 894.6319
DD | NT | S | 10 - DRILLING & COMPL. FLUID | MUD CHEMICALS & ADDITIVES - Section 1 | Sulcis FW-POL 1.1sg conductor hole | M3 | 175 | eur | Volume | 62.6613 | 10965.7246
DD | NT | S | 10 - DRILLING & COMPL. FLUID | MUD CHEMICALS & ADDITIVES - Section 2 | Sulcis FW-POL 1.15sg surface hole | M3 | 255 | eur | Volume | 130.3148 | 33230.2683
OO | NT | S | 10 - DRILLING & COMPL. FLUID | MUD CHEMICALS & ADDITIVES | High vis, LCM pills, kill mud | EA | 14000 | eur | 0 | 1 | 14000
TD | NT | DS | 11 - FLUIDS-SERVICES | MUD UNIT | Mud unit | DAY | 100 | eur | Total drilling time + rig move time | 13.4284 | 1342.8426
TD | NT | DS | 11 - FLUIDS-SERVICES | MUD ENGINEERING PERSONNEL | Mud Engineer (1x) | DAY | 800 | eur | Total drilling time + standby time personnel | 13.9284 | 11142.7407
DD | NT | S | 12 - TREATMENT & DISPOSAL | MUD Liquid Disposal - Section 1 | Sulcis FW-POL 1.1sg conductor hole | M3 | 125.4 | eur | Volume | 62.6613 | 7857.7249
DD | NT | S | 12 - TREATMENT & DISPOSAL | MUD Liquid Disposal - Section 2 | Sulcis FW-POL 1.15sg surface hole | M3 | 125.4 | eur | Volume | 130.3148 | 16341.4731
DD | NT | S | 12 - TREATMENT & DISPOSAL | MUD Cuttings Disposal - all well | All well | M3 | 45 | eur | Well volume | 35.9677 | 1618.5462
TD | NT | DS | 13 - MUD LOGGING | Cabin and personnel - Standby | Cabin and personnel - Standby | DAY | 1330 | eur | All well time plus rigmove time minus drilling time | 7.5783 | 10079.1833
TD | NT | DS | 13 - MUD LOGGING | Cabin and personnel - Operating | Cabin and personnel - Operating | DAY | 2670 | eur | Actual drilling time | 7.5084 | 20047.4972
OO | NT | DS | 14 - DIRECTIONAL DRILLING | LWD/MWD/GYRO | Gyro Survey Charge | EA | 25300 | eur | Total gyro jobs | 1 | 18975
OO | NT | DS | 15 - CORING | CORING | Coring preparation and fixed cost per project | WE | 3500 | eur | Divided by number of wells | 0.5 | 1750
TD | NT | DS | 15 - CORING | CORING | Coring materials (barrel, basket, circ sub, lay down frame, covers, steel tube 9m) | DAY | 855 | eur | Coring days + material standby | 9.614 | 8219.9542
OO | NT | DS | 15 - CORING | CORING | Core head | EA | 20000 | eur | Assume 2x used | 2 | 40000
OO | NT | DS | 15 - CORING | CORING | Core barrel redress charge | EA | 550 | eur | Per core run of 27m | 7 | 3850
OO | NT | DS | 15 - CORING | CORING | Core inner tube 9m for core barrel+plastic container for core transportation+ end caps | EA | 2350 | eur | Per core run of 27m | 7 | 16450
TD | NT | DS | 15 - CORING | CORING | Coring personnel (2x coring eng & 1 x core preservation eng) | DAY | 2750 | eur | Coring days + personnel standby days | 7.614 | 20938.4491
DD | NT | S | 16 - CEMENTING | CEMENTING PRODUCTS - Section 1 | 0-600m - G Cem + Bent + D-Air3000L | M3 | 2000 | eur | section 1 cem volume | 1.1202 | 2240.3661
DD | NT | S | 16 - CEMENTING | CEMENTING PRODUCTS - Section 2 | 0-600m - G Cem + Bent + D-Air3000L | M3 | 500 | eur | section 2 cem volume | 4.3109 | 2155.4543
TD | NT | DS | 16 - CEMENTING | CEMENTING SERVICES | Cementing services (supervisor, operator, helper) - only land | DAY | 1450 | eur | From spud to end of second cement job plus personnel stand-by time | 11.8084 | 17122.2176
TD | NT | DS | 16 - CEMENTING | CEMENTING SERVICES | Cementing equipment stand by | DAY | 2100 | eur | From spud to end of second cement job | 9.8084 | 20597.6944
TD | NT | DS | 16 - CEMENTING | CEMENTING SERVICES | Cementing equipment operating | DAY | 2700 | eur | Actual cementing time | 1 | 2700
DD | T | N | 17 - COMPLETION TUBULARS | TUBING tubular costs Section a | 2 3/8" 4.6# L80 | M | 30 | eur | section a tubing bottom | 300 | 9000
OO | T | N | 18 - COMPLETION-RELATED | TUBING Centralizers Section a | 2 3/8" 4.6# L80 | EA | 130 | eur | tubing section a centralizers # | 3 | 390
TD | NT | N | 18 - COMPLETION-RELATED | TUBING running services | Tubing Running Personnel & Tongs | DAY | 3500 | eur | Completion time + standby time | 4 | 14000
OO | NT | N | 18 - COMPLETION-RELATED | TUBING running services | Mob/Demob fee for equipment & personnel | EA | 4000 | eur | 0 | 1 | 4000
TD | T | N | 18 - COMPLETION-RELATED | TUBING running services | Completion services | DAY | 1200 | eur | Completion time + standby time | 4 | 4800
OO | NT | DS | 19 - WIRELINE | Logging bulk cost | Sulcis logging GR Res Son VSP CBL in 250m | WE | 90000 | eur | 0 | 1 | 90000
OO | NT | S | 20 - LOGISTICS | CASING MATERIALS | transportation round trip all in 1 truck for each well to avoid standby time | WE | 9000 | eur | Per well, as it is more economical to send it back | 1 | 9000
OO | NT | S | 20 - LOGISTICS | CEMENTING MATERIALS | transportation of unit and of material A/R | WE | 15000 | eur | 0 | 1 | 15000
OO | NT | S | 20 - LOGISTICS | MUDLOGGING UNIT | transportation round trip all in 1 truck for 2 wells | WE | 18000 | eur | Divided by number of wells | 0.5 | 9000
OO | NT | S | 20 - LOGISTICS | MUD UNIT AND CHEMICALS | transportation to and from site | WE | 18000 | eur | Divided by number of wells | 0.5 | 9000
OO | NT | S | 20 - LOGISTICS | FISHING EQUIPMENT | transportation round trip all in 1 truck for 2 wells | WE | 9000 | eur | Divided by number of wells | 0.5 | 4500
OO | NT | S | 20 - LOGISTICS | CORING EQUIPMENT | Trasportation of coring equipment and cores | WE | 9000 | eur | Per truck | 1 | 9000
OO | NT | S | 20 - LOGISTICS | SLICKLINE | Slickline Truck | WE | 9000 | eur | Only for well where used | 1 | 9000
TD | NT | GA | 21 - OPERATOR PERSONNEL | Well engineer | 4 months prior to 1 month after the project; also, 15 days of scattered work for lead items | DAY | 800 | eur | Note: Divided by number of wells where necessary | 97.5868 | 78069.4074
TD | NT | GA | 21 - OPERATOR PERSONNEL | Completion engineer | 2 months prior to 15 days after the project; also, 15 days of scattered work for lead items | DAY | 800 | eur | Note: Divided by number of wells where necessary | 60.0868 | 48069.4074
TD | NT | GA | 21 - OPERATOR PERSONNEL | Drilling supervisor | Total well time plus rig move plus 5 days for extra meetings | DAY | 1000 | eur | totwelltime+RigMoveTime+5 | 20.0868 | 20086.7593
TD | NT | GA | 21 - OPERATOR PERSONNEL | Servizio di sorveglianza (HSE) (incl 2x personnel) | 1 x project time | DAY | 500 | eur | 0 | 15.0868 | 7543.3796
TD | NT | GA | 21 - OPERATOR PERSONNEL | direttore dei lavori | 15 days prior to 15 days after the project | DAY | 800 | eur | Note: Divided by number of wells where necessary | 30.0868 | 24069.4074
TD | NT | GA | 21 - OPERATOR PERSONNEL | Guardiania 24hr (incl 2x personnel) | Project time | DAY | 700 | eur | 0 | 15.0868 | 10560.7315
OO | NT | S | 22 - OTHER | INSURANCE | Well Insurance | WE | 20000 | eur | 1 | 1 | 20000

## costs deviated
once off (OO); time-dependent (TD); depth-dependent (DD) | Tangible (T); not-tangible (NT) | Spreadrate (S); drilling spreadrate (DS); G&A (GA); not spreadrate (N) | Class | Subclass | ITEM | UNIT (Well(WE), Item (EA), meters, etc) | Unit Price | Currency | Qty Description | Qty | Total in eur
[10 empty] | TOTAL --> | 1324087.1351
OO | NT | N | 01 - LOCATION | Location preparation | Massenza rig | WE | 26000 | eur | 0 | 1 | 26000
OO | NT | N | 01 - LOCATION | Location restoration | Massenza rig | WE | 30000 | eur | 0 | 1 | 30000
OO | NT | N | 02 - MOB/DEMOB & RIG MOVE | MOB/DEMOB | Massenza rig | PR | 220000 | eur | Wells to drill | 0.5 | 110000
OO | NT | N | 02 - MOB/DEMOB & RIG MOVE | RIG MOVE | Massenza rig | WE | 35000 | eur | Wells to drill | 0.5 | 17500
TD | NT | S | 03 - RIG | RIG FUEL | Massenza rig | DAY | 1500 | eur | Total well time+Rig move time/2 | 14.3556 | 21533.3439
TD | NT | S | 03 - RIG | RIG RATE | Massenza rig | DAY | 9000 | eur | Total well time | 13.6056 | 122450.0633
OO | T | N | 04 - WELL TOP | WELLHEAD | Sulcis 13 3/8" WHH | WE | 30000 | eur | 0 | 1 | 30000
OO | T | N | 04 - WELL TOP | XMAS TREE | Sulcis 13 3/8" Xmas tree | WE | 30000 | eur | 0 | 1 | 30000
TD | NT | S | 04 - WELL TOP | XMAS TREE services | 1 operator including time | DAY | 1200 | eur | Xmas tree setting time + standby time | 3 | 3600
TD | NT | DS | 05 - CASING TUBULARS | CASING RUNNING PERSONNEL | Personnel | DAY | 3400 | eur | Casing Running Time + Time in between two casing runs+Standby time personnel | 9.5081 | 32327.4128
TD | NT | DS | 05 - CASING TUBULARS | CASING RUNNING Material - Standby | Tongs | DAY | 1125 | eur | Material standby time material upon arrival&departure and during drilling hole between two casing jobs | 9.4666 | 10649.9633
TD | NT | DS | 05 - CASING TUBULARS | CASING RUNNING Material - Operating | Tongs | DAY | 2250 | eur | Casing Running Time | 3 | 6750
DD | T | N | 05 - CASING TUBULARS | CASING tubular costs Section 1 | 13 3/8" 72# L80 | M | 178 | usd | section 1 tubular length | 32 | 4784.64
DD | T | N | 05 - CASING TUBULARS | CASING tubular costs Section 2 | 6 5/8" 24# casing with ad hoc centralizer | M | 60 | usd | section 2 tubular length | 238 | 11995.2
OO | T | N | 06 - CASING-RELATED | CASING MATERIAL - OTHER | Float and shoetrack equipment | EA | 6000 | eur | Casing Sections | 2 | 12000
OO | T | N | 06 - CASING-RELATED | CASING Centralizers Section 1 | 13 3/8" 72# L80 | EA | 179 | usd | section 1 centralisers # | 2.6667 | 400.96
OO | T | N | 06 - CASING-RELATED | CASING Centralizers Section 2 | 6 5/8" 24# casing with ad hoc centralizer | EA | 400 | usd | section 2 centralisers # | 13.2222 | 4442.6667
OO | NT | S | 07 - BITS | DRILLING BITS Section 1 | Sulcis deviated 17 1/2" 1.1.1 | EA | 6000 | eur | 0 | 1 | 6000
OO | NT | S | 07 - BITS | DRILLING BITS Section 2 | Sulcis deviated 12 1/4" 4.4.7 | EA | 10000 | eur | 0 | 1 | 10000
OO | NT | DS | 08 - FISHING | Fishing tools package on site | Deviated well 12 1/4" to 270m + 6 5/8" csg | WE | 24500 | eur | 1 | 1 | 24500
TD | NT | DS | 09 - DRILLING | Extra 2 7/8" or 2 3/8" DP daily rental | 4eur/joint/day | DAY | 140.2667 | eur | Total welltime + rigmove time | 15.1056 | 2118.8069
OO | NT | S | 09 - DRILLING | Extra 2 7/8" or 2 3/8" DP final inspection (at end of all wells) | Xovers and subs | ea | 3000 | eur | Divided by number of wells | 0.5 | 1500
DD | NT | S | 09 - DRILLING | WATER | Water supply | M3 | 10 | eur | Total cubic meters | 265.4675 | 2654.6752
TD | NT | S | 09 - DRILLING | Rome soap dope | Rome soap dope | DAY | 100 | eur | Total drilling time | 11.0681 | 830.1047
DD | NT | S | 10 - DRILLING & COMPL. FLUID | MUD CHEMICALS & ADDITIVES - Section 1 | Sulcis FW-POL 1.1sg conductor hole | M3 | 175 | eur | Volume | 65.4312 | 11450.4584
DD | NT | S | 10 - DRILLING & COMPL. FLUID | MUD CHEMICALS & ADDITIVES - Section 2 | Sulcis FW-POL 1.3sg surface hole | M3 | 255 | eur | Volume | 142.5082 | 36339.5883
DD | NT | S | 10 - DRILLING & COMPL. FLUID | BRINE | Brine at completion stage | M3 | 50 | eur | Total brine volume | 60 | 3000
OO | NT | S | 10 - DRILLING & COMPL. FLUID | MUD CHEMICALS & ADDITIVES | High vis, LCM pills, kill mud | EA | 14000 | eur | 0 | 1 | 14000
TD | NT | DS | 11 - FLUIDS-SERVICES | MUD UNIT | Mud unit | DAY | 100 | eur | Total drilling time + rig move time | 12.5681 | 1256.8063
TD | NT | DS | 11 - FLUIDS-SERVICES | MUD ENGINEERING PERSONNEL | Mud Engineer (1x) | DAY | 800 | eur | Total drilling time + standby time personnel | 13.0681 | 10454.4501
DD | NT | S | 12 - TREATMENT & DISPOSAL | MUD Liquid Disposal - Section 1 | Sulcis FW-POL 1.1sg conductor hole | M3 | 125.4 | eur | Volume | 65.4312 | 8205.0713
DD | NT | S | 12 - TREATMENT & DISPOSAL | MUD Liquid Disposal - Section 2 | Sulcis FW-POL 1.3sg surface hole | M3 | 182 | eur | Volume | 142.5082 | 25936.4905
DD | NT | S | 12 - TREATMENT & DISPOSAL | MUD Cuttings Disposal - all well | All well | M3 | 45 | eur | Well volume | 77.9306 | 3506.8776
DD | T | GA | 12 - TREATMENT & DISPOSAL | Brine disposal | Brine disposal | M3 | 80 | eur | 0 | 60 | 4800
TD | NT | DS | 13 - MUD LOGGING | Cabin and personnel - Standby | Cabin and personnel - Standby | DAY | 1330 | eur | All well time plus rigmove time minus drilling time | 8.9989 | 11968.575
TD | NT | DS | 13 - MUD LOGGING | Cabin and personnel - Operating | Cabin and personnel - Operating | DAY | 2670 | eur | Actual drilling & reaming time | 6.1066 | 16304.7128
TD | NT | DS | 14 - DIRECTIONAL DRILLING | Mud motor + MWD Daily rental fee - Section 2 | Sulcis 12 1/4" deviated PDM - Baker | DAY | 1680 | eur | Material stand by time | 4 | 7392
TD | NT | DS | 14 - DIRECTIONAL DRILLING | Mud motor + MWD Usage fee - Section 2 | Sulcis 12 1/4" deviated PDM - Baker | DAY | 6585 | eur | Actual directional drilling time | 2.0722 | 15010.1417
TD | NT | DS | 14 - DIRECTIONAL DRILLING | Personnel - Section 2 | Sulcis 12 1/4" deviated PDM - Baker | DAY | 3600 | eur | section 2 drilling | 4.0722 | 16126
OO | NT | DS | 14 - DIRECTIONAL DRILLING | LWD/MWD/GYRO | Gyro Survey Charge | EA | 25300 | eur | Total gyro jobs | 1 | 18975
OO | NT | DS | 15 - CORING | CORING | Coring preparation and fixed cost per project | WE | 3500 | eur | Divided by number of wells | 0.5 | 1750
TD | NT | DS | 15 - CORING | CORING | Coring materials (barrel, basket, circ sub, lay down frame, covers, steel tube 9m) | DAY | 855 | eur | Coring days + material standby | 5.6412 | 4823.2416
OO | NT | DS | 15 - CORING | CORING | Core head | EA | 20000 | eur | 1 | 1 | 20000
OO | NT | DS | 15 - CORING | CORING | Core barrel redress charge | EA | 550 | eur | Per core run of 27m | 1 | 550
OO | NT | DS | 15 - CORING | CORING | Core inner tube 9m for core barrel+plastic container for core transportation+ end caps | EA | 2350 | eur | Per core run of 27m | 1 | 2350
TD | NT | DS | 15 - CORING | CORING | Coring personnel (2x coring eng & 1 x core preservation eng) | DAY | 2750 | eur | Coring days + personnel standby days | 3.6412 | 10013.3501
DD | NT | S | 16 - CEMENTING | CEMENTING PRODUCTS - Section 1 | 0-600m - G Cem + Bent + D-Air3000L | M3 | 2000 | eur | section 1 cem volume | 2.4845 | 4969.0406
DD | NT | S | 16 - CEMENTING | CEMENTING PRODUCTS - Section 2 | Evercrete Schlumberger for CO2 seal | M3 | 3000 | eur | section 2 cem volume | 17.1721 | 51516.284
TD | NT | DS | 16 - CEMENTING | CEMENTING SERVICES | Cementing services (supervisor, operator, helper) - only land | DAY | 1450 | eur | From spud to end of second cement job plus personnel stand-by time | 10.5481 | 15294.6908
TD | NT | DS | 16 - CEMENTING | CEMENTING SERVICES | Cementing equipment stand by | DAY | 2100 | eur | From spud to end of second cement job | 8.5481 | 17950.9314
TD | NT | DS | 16 - CEMENTING | CEMENTING SERVICES | Cementing equipment operating | DAY | 2700 | eur | Actual cementing time | 1 | 2700
DD | T | N | 17 - COMPLETION TUBULARS | TUBING tubular costs Section a | 2 3/8" 4.6# L80 | M | 30 | eur | section a tubing bottom | 316 | 9480
OO | T | N | 18 - COMPLETION-RELATED | TUBING Centralizers Section a | 2 3/8" 4.6# L80 | EA | 130 | eur | tubing section a centralizers # | 3 | 390
TD | NT | N | 18 - COMPLETION-RELATED | Slickline | Slickline Personnel & crew | DAY | 3000 | eur | Slickline time +standby time | 3 | 9000
OO | NT | N | 18 - COMPLETION-RELATED | Slickline | Mob/Demob for equipment & personnel | EA | 2000 | eur | Only if slickline | 1 | 2000
TD | NT | N | 18 - COMPLETION-RELATED | TUBING running services | Tubing Running Personnel & Tongs | DAY | 3500 | eur | Completion time + standby time | 4 | 14000
OO | NT | N | 18 - COMPLETION-RELATED | TUBING running services | Mob/Demob fee for equipment & personnel | EA | 4000 | eur | 0 | 1 | 4000
TD | T | N | 18 - COMPLETION-RELATED | TUBING running services | Completion services | DAY | 1200 | eur | Completion time + standby time | 4 | 4800
OO | T | N | 18 - COMPLETION-RELATED | Completion EQUIPMENT | Sulcis deviated well | WE | 42750 | eur | 0 | 1 | 42750
OO | NT | DS | 19 - WIRELINE | Logging bulk cost | Sulcis logging GR Res Son VSP CBL in 250m | WE | 100000 | eur | 0 | 1 | 100000
OO | NT | S | 20 - LOGISTICS | CASING MATERIALS | transportation round trip all in 1 truck for each well to avoid standby time | WE | 9000 | eur | Per well, as it is more economical to send it back | 1 | 9000
OO | NT | S | 20 - LOGISTICS | CEMENTING MATERIALS | transportation of unit and of material A/R | WE | 15000 | eur | 0 | 1 | 15000
OO | NT | S | 20 - LOGISTICS | MUDLOGGING UNIT | transportation round trip all in 1 truck for 2 wells | WE | 18000 | eur | Divided by number of wells | 0.5 | 9000
OO | NT | S | 20 - LOGISTICS | MUD UNIT AND CHEMICALS | transportation to and from site | WE | 18000 | eur | Divided by number of wells | 0.5 | 9000
OO | NT | S | 20 - LOGISTICS | FISHING EQUIPMENT | transportation round trip all in 1 truck for 2 wells | WE | 9000 | eur | Divided by number of wells | 0.5 | 4500
OO | NT | S | 20 - LOGISTICS | CORING EQUIPMENT | Trasportation of coring equipment and cores | WE | 9000 | eur | Per truck | 1 | 9000
OO | NT | S | 20 - LOGISTICS | DIRECTIONAL DRILLING round trip | Sulcis 12 1/4" deviated PDM - Baker | WE | 6000 | eur | Per well, as it is more economical to send it back | 1 | 6000
OO | NT | S | 20 - LOGISTICS | SLICKLINE | Slickline Truck | WE | 9000 | eur | Only for well where used | 1 | 9000
TD | NT | GA | 21 - OPERATOR PERSONNEL | Well engineer | 4 months prior to 1 month after the project; also, 15 days of scattered work for lead items | DAY | 800 | eur | Note: Divided by number of wells where necessary | 97.6056 | 78084.4501
TD | NT | GA | 21 - OPERATOR PERSONNEL | Completion engineer | 2 months prior to 15 days after the project; also, 15 days of scattered work for lead items | DAY | 800 | eur | Note: Divided by number of wells where necessary | 60.1056 | 48084.4501
TD | NT | GA | 21 - OPERATOR PERSONNEL | Drilling supervisor | Total well time plus rig move plus 5 days for extra meetings | DAY | 1000 | eur | totwelltime+RigMoveTime+5 | 20.1056 | 20105.5626
TD | NT | GA | 21 - OPERATOR PERSONNEL | Servizio di sorveglianza (HSE) (incl 2x personnel) | 1 x project time | DAY | 500 | eur | 0 | 15.1056 | 7552.7813
TD | NT | GA | 21 - OPERATOR PERSONNEL | direttore dei lavori | 15 days prior to 15 days after the project | DAY | 800 | eur | Note: Divided by number of wells where necessary | 30.1056 | 24084.4501
TD | NT | GA | 21 - OPERATOR PERSONNEL | Guardiania 24hr (incl 2x personnel) | Project time | DAY | 700 | eur | 0 | 15.1056 | 10573.8938
OO | NT | S | 22 - OTHER | INSURANCE | Well Insurance | WE | 20000 | eur | 1 | 1 | 20000